## DCIP Cover Page
LEA Name: | Mt. Morris Central School District | ENTER DATA INTO ALL YELLOW CELLS.
BEDS Code: | 240901040000
2018-2019 District Comprehensive Improvement Plan (DCIP)
Contact Name | Mr. Gregory Bump | Title | Superintendent of Schools
Phone | 585-658-5036 | Email | gbump@mtmorriscsd.org
Website for Published Plan | https://www.mtmorriscsd.org
APPROVAL OF THIS PLAN BY THE SUPERINTENDENT AND BOARD OF EDUCATION (IN NEW YORK CITY, THE CHANCELLOR OR THE CHANCELLOR’S DESIGNEE) IS MANDATORY.
Implementation is required no later than the first day of regular student attendance.
Signatures confirm the respective parties certify that the DCIP addresses all of the required components of the ESSA and Commissioner's Regulations as detailed on page 1 of this document and understand that any significant modification of the school district’s approved plan require the prior approval of the commissioner.
THE SIGNATURES BELOW CONFIRM APPROVAL.
Position | Signature | Print Name | Date
Superintendent |  | Greg Bump
President, B.O.E. / Chancellor or Chancellor's Designee |  | Pete Privitera

## Assurances
Statement of Assurances
By signing this document, the Local Education Agency certifies that:
x | 1. The District Comprehensive Improvement Plan (DCIP) has been developed in consultation with parents, school staff and others in accordance with the requirements of Shared-Decision Making (CR 100.11) to provide a meaningful opportunity for stakeholders to participate in the development of the plan and comment on the plans before they are approved.
x | 2. The District Comprehensive Improvement Plan (DCIP) has been formally approved by the school board and will be made widely available through public means, such as posting on the Internet, distribution through the media and distribution through public agencies.
x | 3. The District Comprehensive Improvement Plan (DCIP) will be implemented no later than the beginning of the first day of regular student attendance.
x | 4. A comprehensive systems approach will be established to recruit, develop, retain and equitably distribute effective teachers and school leaders as part of the implementation of the Annual Professional Performance Review (APPR) system required by Education law §3012(c) and §3012(d).
x | 5. Professional development will be provided to teachers and school leaders that will fully support the strategic efforts described within this plan.
x | 6.Meaningful time for collaboration will be used to review and analyze data in order to inform and improve district policies, procedures, and instructional practices.

## District Leadership Team
District Leadership Team
DISTRICT LEADERSHIP TEAM: The DCIP must be developed in consultation with parents, school staff, and others pursuant to §100.11 of Commissioner’s Regulations. Participants who are regularly involved in your district and school improvement initiatives, such as community organizations or institutes of higher education should be included. By signing below, stakeholders ascertain that, although they may not agree with all components of the plan, they have actively participated in the development and revision of the DCIP.
Instructions: List the stakeholders who participated in developing the DCIP as required by Commissioner’s Regulations §100.18. Provide dates and locations of Local Stakeholder meetings. Boxes should be added as necessary.
Meeting Date(s) | Locations(s) | Meeting Date(s) | Location(s)
2018-06-05 | Principal's Conference Room
2018-06-12 | Principal's Conference Room
2018-06-19 | Parent Feedback Input Session
2018-07-17 | Parent Feedback Input Session
Name | Title / Organization |  | Signature
Christine Caskey | Elementary Teacher
Brittany Chapman | H.S. Teacher
Danielle Dean | Elementary Teacher
Rachael Greene | Elementary Principal
Sarah Levy | Reading Teacher
Sarah Sheffield | H.S. Spanish Teacher
Judy Wheeler | Computer Technology Teacher
Gregory Bump | Superintendent of Schools
Tamara Lipke | Associate, PLC Associates, Inc.
Jesse Hamilton | Jr./Sr. High School Principal
David Provo | Parent

## Overview
| DCIP Plan Overview | REVIEWER FEEDBACK
In this section, the district must describe the development of the plan, the degree to which the previous school year's DCIP was successfully implemented, overall improvement mission or guiding principles at the core of the strategy for executing the mission/guiding principles, the key design elements of the DCIP, and other unique characteristics of the plan (if any), and provide evidence of the district’s capacity to effectively oversee and manage the improvement plan.
The DCIP must be made widely available through public means, such as posting on the Internet, by the district. The Overview will serve as the at-a-glance summary of how the district will use various funding sources to improve student achievement. A complete overview will address the following:
1. Rate the degree to which the District achieved the goals identified in the previous year's District Comprehensive Improvement Plan (Mark with an "X").
Limited Degree (Fewer than 20% of goals were achieved.)
Partial Degree (Fewer than 50% of goals were achieved.)
X | Moderate Degree (At least 50% of goals were achieved.)
Major Degree (At least 90% of goals were achieved.)
2. Rate the degree to which the District successfully implemented the activities identified in the previous year's DCIP (Mark with an "X").
Limited Degree (Fewer than 20% of activities were carried out.)
Partial Degree (Fewer than 50% of activities were carried out.)
X | Moderate Degree (At least 50% of activities were carried out.)
Major Degree (At least 90% of activities were carried out.)
3. Rate the degree to which the activities identified in the previous year's District Comprehensive Improvement Plan impacted academic achievement targets for identified subgroups (Mark with an "X").
Limited Degree (No identified subgroups improved achievement.)
X | Partial Degree (Some of the identified subgroups improved achievement.)
Moderate Degree (A majority of identified subgroups improved achievement.)
Major Degree (All identified subgroups improved achievement.)
4. Rate the degree to which the activities identified in the previous year's DCIP increased Parent Engagement (Mark with an "X").
Limited Degree (There was no increase in the level of Parent Engagement.)
Partial Degree (There was a minor increase in the level of Parent Engagement.)
Moderate Degree (There was modest increase in the level of Parent Engagement.)
X | Major Degree (There was a significant increase in the level of Parent Engagement.)
5. Rate the degree to which the activities identified in the previous year's District Comprehensive Improvement Plan received the funding necessary to achieve the corresponding goals (Mark with an "X").
Limited Degree (Fewer than 20% of planned activities were funded.)
Partial Degree (Fewer than 50% of planned activities were funded.)
Moderate Degree (At least 50% of planned activities were funded.)
X | Major Degree (At least 90% of planned activities were funded.)
6. Identify in which Tenet the district made the most growth during the previous year (Mark with an "X").
Tenet 1: District Leadership and Capacity
Tenet 2: School Leader Practices and Decisions
Tenet 3: Curriculum Development and Support
Tenet 4: Teacher Practices and Decisions
Tenet 5: Student Social and Emotional Developmental Health
X | Tenet 6: Family and Community Engagement
7. Identify in which Tenet identified schools made the most growth during the previous year (Mark with an "X").
Tenet 1: District Leadership and Capacity
Tenet 2: School Leader Practices and Decisions
Tenet 3: Curriculum Development and Support
Tenet 4: Teacher Practices and Decisions
Tenet 5: Student Social and Emotional Developmental Health
X | Tenet 6: Family and Community Engagement
In reflecting on the PREVIOUS YEAR'S PLAN:
• Describe the most significant positive impact(s) that resulted from the previous year’s plan (may include such examples as specific changes in adult behavior and/or measurable changes in student outcomes).
Parent engagement increased significantly.
• Describe all mid-course corrections to the previous year’s plan in response to data review and needed adjustment. Include details of current impact and expectations for sustainability moving forward.
Grandparent workshops were offered.
In developing the CURRENT YEAR'S plan:
• List the highlights of the improvement initiatives described in the current DCIP.
Increased shared ownership of our school and building plan. Increase data driven decisionmaking. Develop higeer order question
• List the identified needs in the district that will be targeted for improvement in this plan.
Communication, Planning, Instruction,
• State the mission or guiding principles of the district and describe the relationship between the mission or guiding principles and the identified needs of the district.
The district's mission is " At Mount Morris Central School District we are building the future, laying the foundation of lifelong learning, opening minds to explore, to create, and to achieve excellence." The initiatives outlined in the plan will lead to academic excellence for all learners.
• List the student academic achievement targets for the identified subgroups in the current plan.
Levels 3 & 4 on state assessments, on grade level reading in the IRLA
• Describe how organizational structures will drive strategic implementation of the mission/guiding principles.
The district has a building leadership team which will drive much of the initiative work. The team is comprised of two Master teachers (one at the elementary level and one at the Jr/Sr high level), a teacher leader for special education, a teacher leader for PBIS, and a teacher leader for instructional technology. The district also has a school level SCEP team which oversees the implementation of the SCEP and DCIP plans. The Shared Decision Making Team also plays a role in monitoring the implementation of the plans.
• List anticipated barriers that may impact the ability to accomplish the mission or guiding principles and how those barriers will be addressed.
staff participation, parent involvement, leadership turnover, teacher turnover
• Describe the professional development opportunities that will be provided to teachers and school leaders and the rationale for each opportunity.
Parent workshops, student ownership of learning/learning targets, Webb's depth of knowldege and increasing levels of rigor in units and lessons
• List all methods of dialogue that district leaders will implement to strengthen relationships with school staff and the community.
Faculty meetings and weekly communication to school staff will regularly occur. Monthly newsletters to families.
• List all the ways in which the current plan will be made widely available to the public.
The plan will be posted on the district's website at www.mtmorriscsd.org

## Tenet 1
Tenet 1: District Leadership and Capacity |  |  | REVIEWER FEEDBACK
Tenet 1: District Leadership and Capacity |  | The district examines school systems and makes intentional decisions to identify and provide critical expectations, supports and structures in all areas of need so that schools are able to respond to their community and ensure that all students are successful. | The district examines school systems and makes intentional decisions to identify and provide critical expectations, supports and structures in all areas of need so that schools are able to respond to their community and ensure that all students are successful.
B1. Most Recent DTSDE Review Date: |  | 2018-05-01
B2. DTSDE Review Type: |  | District-Led Focus Visit
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | Based upon the 2018 District self-reflection, there has been a sustained focus on communication to parents and the larger community, however, there is not the degree of shared ownership for the DCIP and SCEP plans across stakeholder groups. The district needs to clarify and enhance communication systems to increase shared ownership of the work of the SCEP and DCIP and ongoing monitoring for effectiveness.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, the district will have increased shared ownership for the monitoring and implementation of the SCEP and DCIP as measured by an increase in responses to the five items listed below. A baseline measure will occur in September 2018 with follow-up measurement mid-year and end-of-year 2019: 1. I have a clear understanding of the work outlined in the SCEP (K-6). 2. I have a clear understanding of the work outlined in the DCIP (K-12). 3. I understand my role in implementing the SCEP (K-6). 4. I understand my role in implementing the DCIP (K-12). 5. I understand the connections between our initiatives and the goals of the SCEP and DCIP (K-12).
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Meeting Agendas and Minutes from SCEP and DCIP team meetings Quarterly Reports documenting progress towards goals and shared with faculty
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-07-01 | 2018-08-01 | Activity: During new leader induction, the leadership team will review, discuss, and calendar the 2018-19 SCEP and DCIP plans Responsible: Superintendent Participants: Superintendent, Elementary and High School Principals Frequency: Once Intended Impact: Greater understanding for the leaderhsip team of all aspects of the plans to better support implementation
2018-07-18 | 2018-08-18 | Activity: The leadership team will meet to discuss and determine rebranding and common language for references to and implementation of the SCEP and DCIP Responsible: Superintendent Participants: Superintendent and Principals Frequency: 1-2 meetings Intended Impact: Streamline district processes and increase communication and understanding of the plans through the use of common language
2018-09-18 | 2018-05-19 | Activity: At the beginning of each conference day an introduction to the day will occur and include district-level communication connecting the focus for the day to the goal/focus of the SCEP and DCIP Responsible: Superintendent and Building Leaders Participants: Superintendent, Building Leaders, Teachers Frequency: at least 4x/year Intended Impact: Explicit communication about the connections between the work, PD and SCEP/DCIP will increase understanding of the purpose for the work
2018-09-18 | 2018-05-19 | Activity: Building level meetings will establish a focus and connection will be made to either the SCEP and/or DCIP work Responsible: Building leaders Participants: Building leaders and Teachers Frequency: each meeting Intended Impact: Increase faculty and staff understanding and ownership for the focused work connected to the SCEP and DCIP
2018-09-18 | 2018-05-19 | Activity: The SCEP and DCIP teams(s) will meet regularly to analyze data, monitor and adjust to support progress toward the goals. At these meetings, a next step will include communication to the larger faculty/staff regarding progress. Responsible: Building leaders Participation: SCEP/DCIP teams, bulding leaders and teachers Frequency: at least 4 x/year Intended Impact: Increased communication and ownership will occur as progress along the way is regularly published.

## Tenet 2
Tenet 2: School Leader Practices and Decisions |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 2.1 - The district works collaboratively with the school to provide opportunities and supports for the school leader to create, develop and nurture a school environment that is responsive to the needs of the entire school community. | SOP 2.1 - The district works collaboratively with the school to provide opportunities and supports for the school leader to create, develop and nurture a school environment that is responsive to the needs of the entire school community.
B1. Most Recent DTSDE Review Date: |  | 2018-05-01
B2. DTSDE Review Type: |  | District-led Focus Visit
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | In order for the District to work collaboratively with the schools to create, develop, and nurture a school environment to success, well-being and high academic outcomes for all students, the District needs to provide training and supports regarding the collection of data, provision of feedback, identification of meaningful and relevant professional development and monitoring systems for the purpose of continuous school improvement. In the School Performance Scan survey, 91% of respondents reported that school leaders frequently visit classrooms, conducting informal walkthroughs. Likewise, 76% of teachers indicate that they receive instructional feedback and guidance from school leaders, but only 68% indicated that their school utilizes a comprehensive, school-wide system that includes a Data Dashboard for monitoring goals and progress. The District must establish high expectations for connecting the use of data to identify research-based professional practices matched to student outcomes.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, all School Leaders will have collected, recorded and published school-wide data. Individual school data will demonstrate an 10% increase in implementation of three out of 4 Look-Fors from September to June.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | School learning walk tool data summary reports
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-08-01 | 2019-08-01 | Activity: School leaders will be provided with Leveraged Leadership Program, and in-depth training on identification and evidence collection around District Instructional Look-Fors. Responsible: Educational Consultant Participants: School leaders Frequency: 6-8 sessions Intended Impact: School leaders can recognize and evaluate the efficacy of each Look-For.
2018-08-18 | 2018-10-18 | Activity: School leaders will select 4 Look-Fors for which the leaders will collect school-wide data Responsible: Consultant Participation: School leaders Frequency: one time Intended Impact: All Learning Walk data is focused on district-wide identified areas
2018-08-18 | 2018-10-18 | Activity: A District-wide Data Dashboard will be created to share information with staff Responsible: Consultant Participation: School leaders Frequency: one time Intended Impact: School leaders will have a consistent venue to share school-wide data
2018-08-18 | 2018-10-18 | Activity: The School leaders will create a timeline for sharing information from the Data Dashboard Responsible: Consultant Participation: School leaders Frequency: one time Intended Impact: School leaders will establish a consistent timeline for communicating school data
2018-08-18 | 2018-10-18 | Activity: School leaders will select one Data Collection Protocol (technology tool) to be used by all school leaders Responsible: Consultant Participation: School leaders Frequency: one time Intended Impact: All Learning Walk data is collected in the same platform so district-wide reporting may be done
2018-08-18 | 2018-10-18 | Activity: School leaders will be provided with in-depth training on the use of the selected Data Collection Protocol and Platform Responsible: Consultant Participation: School Leaders Frequency: One session Intended Impact: School leaders can routinely and accurately collect and record school-level Learning Walk data
2018-10-18 | 2018-06-19 | Activity: School leaders will conduct Learning Walks throughout the school building and gather data based on the identified Look-Fors Responsible: School leaders Participation: School leaders Frequency: 10 learning walks per week Intended Impact: School leaders will gather data to inform decision making

## Tenet 3
Tenet 3: Curriculum Development and Support |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 3.1 - The district works collaboratively with the school(s) to ensure CCLS curriculum that provide 21st Century and College and Career Readiness skills in all content areas and provides fiscal and human resources for implementation. | SOP 3.1 - The district works collaboratively with the school(s) to ensure CCLS curriculum that provide 21st Century and College and Career Readiness skills in all content areas and provides fiscal and human resources for implementation.
B1. Most Recent DTSDE Review Date: |  | 2018-05-18
B2. DTSDE Review Type: |  | District-led Focus Visit
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | In order to increase curriculum planning for levels of complexity and rigor, there is a need for more students involved in higher-level thinking across the content areas. According to the School Performance Scan 86% of the teachers state that the school is student-centered. However, student performance isn’t demonstrating proficiency in formative assessments. As a result, there is a disconnect in the utilization and effectiveness in higher-level thinking strategies across the content areas.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, instructional staff members will explicitly plan and implement higher order thinking questions that promote cognitive complexity and intellectual discovery, resulting in increased higher-level thinking by the students. As measured by the availability of high quality scope and sequence documents, which include higher order thinking activites, at the rate of at least two content/courses per teacher.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Staff attendance at Professional Development Classroom Visit Tool Formative Assessments
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-18 | 2018-10-18 | Activity: Professional learning targeting Webb’s Depth of Knowledge Model Responsible: School Leader Participants: All instructional staff Frequency: one meeting Intended Impact: improved student engagement and use of higher order thinking questions in classroom instruction
2018-11-18 | 2018-01-19 | Activity: Refresher and continuation of Professional learning targeting Webb’s Depth of Knowledge Model Responsible: School Leader Participants: All instructional staff Frequency: 2 times Intended Impact: improved student engagement and use of higher order thinking questions in classroom instruction
2018-09-18 | 2018-09-18 | Activity: Create a shared space for all preK-12 content areas to share scope and sequencing Responsible: School Leadership Team Participants: School Leadership Team Frequency: one time Intended Impact: shared space for curriculum alignment
2018-09-18 | 2018-10-18 | Activity: Develop and communicate with instructional staff expectations of sharing scope and sequence work Responsible: School Leadership Team Participants: instructional staff Frequency: one time Intended Impact: collaborating shared space for curriculum alignment
2018-11-18 | 2018-06-19 | Activity: Develop and revise grades 7-12 scope and sequence plans to include high quality higher order thinking experiences in at least two prioritized areas. Responsible: Classroom teachers Participants: classroom teachers Frequency: 3 days per year Intended Impact: Improved student engagement and higher order thinking
2018-11-18 | 2018-06-19 | Activity: Implement and revise K-6 scope and sequence to ensure inclusion of higher-order thinking tasks of ELA and math. Consider development of scope and sequence in Science or writing. Responsible: Building leaders Participants: classroom teachers Frequency: 3 days per year Intended Impact: deeper implementation of learning experiences requiring high levels of thinking.
2018-11-18 | 2018-06-19 | Activity: Classroom visits Responsible: Administrators, professional learning consultant and instructional staff Participants: Administrators and teachers Frequency: 10 visits per week Intended Impact: improved student engagement and higher order thinking
2018-08-18 | 2018-09-18 | Activity: The SCEP/DCIP team will develop a system for monitoring the writing and implementation for the scope and sequence. Responsible: SCEP/DCIP team Participants: The team Frequency: one time Intended Impact: monitoring progress to ensure full implementation of a guaranteed, viable curriculum.

## Tenet 4
Tenet 4: Teacher Practices and Decisions |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 4.1 - The district works collaboratively with the school to provide opportunities and supports for teachers to develop strategies and practices and addresses effective planning and account for student data, needs, goals, and levels of engagement. | SOP 4.1 - The district works collaboratively with the school to provide opportunities and supports for teachers to develop strategies and practices and addresses effective planning and account for student data, needs, goals, and levels of engagement.
B1. Most Recent DTSDE Review Date: |  | 2018-05-01
B2. DTSDE Review Type: |  | District-led Focus Visit
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | In order to address the gap between complying and being actively engaged in a lesson, teachers will consistently use multiple engagement strategies to engage students. The learning walk data showed a frequent use of technology during lessons but few other strategies. As a result, we find that we need to assure that all staff understand and consistently use a variety of effective engagement strategies, including strategies that elicit higher levels of student thinking.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June of 2019, 80% of teachers will consistently demonstrate a purposeful use of various engagement strategies to productively engage students at various levels of thinking as measured by Learning Walks.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Learning Walks
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-08-18 | 2018-09-18 | Activity: Provide each new teacher with a copy of Total Participation Techniques 2nd Edition by Persida and William Himmele and develop and communicate expectations for the use and application of the text. Review expectations with all staff for the use of the text at the beginning of the school year. Responsible: School Leaders Participants: School Leaders & Teachers Frequency: once Intended Impact: Provide consistency across the school so all teachers will have access to total participation techniques
2018-09-18 | 2018-01-19 | Activity: Provide professional development on using engagement strategies to activate higher-order thinking Responsible: district leaders, school leaders Participants: districts leaders, school leaders, teachers Frequency: minimum of 2 Intended Impact: Data gathered during Learning Walks should show an increase in the selection of the engagement strategies to increase complexity of thinking used during lessons
2018-09-18 | 2018-04-19 | Activity: Provide learning walks focused on total participation techniques that will build upon previous feedback Responsible: School Leaders, Teacher Leaders Participants: School Leaders, Teachers Frequency: minimum of 3 per year per teacher Intended Impact: Data gathered during Learning Walks should show an increase in the use and quality of the engagement strategies utilized during lessons from one visit to the next

## Tenet 5
Tenet 5: Student Social and Emotional Developmental Health |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 5.1 - The district creates policy and works collaboratively with the school to provide opportunities and resources that positively support students' social and emotional developmental health. | SOP 5.1 - The district creates policy and works collaboratively with the school to provide opportunities and resources that positively support students' social and emotional developmental health.
B1. Most Recent DTSDE Review Date: |  | 2018-05-01
B2. DTSDE Review Type: |  | District-led Focus Visit
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | According to the June 2018 School Performance Scan data, we are lacking a collaborative system for responding to student Social and Emotional Developmental needs (item #61, 66.7%). Data also indicate that student behaviors interfere with instruction (SPS item #69, 9.5%) (Family Engagement Survey #39, 57.8%). The district needs to create and implement a system for coordination and support of SEDH needs.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By May 2019, composite results from the 2019 administration of the School Performance Scan and Family Engagement Surveys will indicate a minimum 5-7% increase in the percentage of respondents reporting that there is an effective system for developing and building Student Social Emotional Health (SPS item #61) and a minimum 5-7% increase in the percentage of respondents reporting that student behavior does not interfere with instruction (SPS item #69, FES #39).
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Survey data Number of staff trained in de-escalation strategies focus group results referral data suspension rates
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-07-01 | 2018-09-18 | Activity: District leaders and PPS team identify roles and responsibilities for PPS Staff Responsible: District leaders and PPS staff Participants: District leaders and PPS staff Frequency: 2 meetings Intended Impact: To clarify roles and responsibilities of PPS staff
2018-08-18 | 2018-09-18 | Activity: District leaders and PPS team communicate roles and responsibilities to staff Responsible: District leaders and PPS staff Participants: District leaders and PPS staff Frequency: 1 faculty meeting Intended Impact: To clarify and communicate roles and responsibilities of PPS staff
2018-07-18 | 2018-05-19 | Activity: District leaders and PPS team will develop and refine a tiered system of social emotional supports to address student SEDH needs. Responsible: District leaders and PPS staff Participants: District leaders and PPS staff Frequency: 2 initial days, and bimonthly meetings Intended Impact: to establish and implement systems and procedures for identifying student SEDH needs at different levels.
2018-09-18 | 2018-10-18 | Activity: Design a system of communication for the tiered system of social emotional support Responsible: District Leaders and PPS Staff Participants: All faculty and staff Frequency: one time Intended Impact: to increase understanding and improve implementation of the systems and procedures to support student social emotional needs.
2018-07-18 | 2018-08-18 | Activity: District will schedule and provide for Level 3 TCIS Certification for Building level administrators and PPS Staff Responsible: District administration Participation: Building level administrators, PPS Staff, TCIS trainers Frequency: 5 full days Intended Impact: to increase the number of people trained in TCIS to support and address student behaviors and SEDH needs.
2018-08-18 | 2018-03-19 | Activity: District will schedule and provide for TCIS-based training in de-escalation strategies for all special education teachers, general education teachers, and support staff Responsible: District Administration Participants: All teachers, aides, and TCIS trainers Frequency: a schedule will be developed Intended Impact: increase the number of people trained in TCIS-based de-escalation strategies, in order to reduce student behaviors that interfere with instruction.
2018-10-18 | 2018-03-19 | Activity: District Leadership Team will create and implement data collection tool Responsible: Building Leadership Team Participants: All teachers and staff, family focus group Frequency: November, March Intended Impact: monitor impact of systems and professional development and adjust action steps as needed.

## Tenet 6
Tenet 6: Family and Community Engagement |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 6.1 - The district has a comprehensive family and community engagement strategic plan that states the expectations around creating and sustaining a welcoming environment for families, reciprocal communication, and establishing partnerships with community organizations and families. | SOP 6.1 - The district has a comprehensive family and community engagement strategic plan that states the expectations around creating and sustaining a welcoming environment for families, reciprocal communication, and establishing partnerships with community organizations and families.
B1. Most Recent DTSDE Review Date: |  | 2018-05-01
B2. DTSDE Review Type: |  | District-led Focus Visit
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | Based on the School Performance Scan, 68% of respondents indicated that the District has conducted a needs assessment with families to build an understanding of the interests and concerns. Therefore, the district needs to seek further input from parents and families in order to target their needs through planned workshops and events.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, the district will conduct a needs assessment, analyze the results and plan at least two programs to meet the identified needs.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | needs assessment exit ticket for each of the events
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-18 | 2018-11-18 | Activity: The District Leadership will develop and administer a needs assessment to families Responsible: Building and District Leadership team Participants: Building and District Leadership Teams Frequency: 1 meeting Intended Impact: To develop a tool for soliciting parent input on their needs
2018-11-18 | 2018-11-18 | Activity: Implement, gather, and analyze the data from the needs assessment to identify priority areas. Responsible: Building and District leadership teams Participants: Shared Decision-making teams Frequency: 2 meetings Intended Impact: Identifying needs areas in order to plan for targeted parent events.
2018-12-19 | 2018-05-19 | Activity: Plan and implement parent workshop or event (including an exit ticket) focused on the priority need areas Responsible: Building and District Leadership Teams Participants: Building and Leadership teams and parents Frequency: 2 planning mtgs and two events Intended Impact: Parent understanding and use of strategies in support of their children will improve

## AllocationPlan-Improvement
Financial Allocation Plan - Improvement
Improvement Set-Aside Budget Summary
District | Accountability Status | Amount of Funds Allocated for District-Level Improvement
Mount Morris Central School District | Focus District | 50000
Name of Priority/Focus School | Accountability Status | Amount of Funds Allocated for School-Level Improvement
Mount Morris Elementary School | Focus School | 50000
DISTRICT / BUILDING TOTALS |  | 100000

## SI Set Aside Rates (hidden)
School Improvement Set Aside Rate based on count of all schools
LEA BEDS | LEA NAME | All Schools | # of Priority & Focus Schools (minimum required) | % of identified schools | Required Set Aside % | Title III Set Aside required | Percentage of identified schools | Required Set-Aside rate
010100010000 | ALBANY CITY SD | 15 | 13 | 86.67% | 15% |  | Less than 30% | 5%
270100010000 | AMSTERDAM CITY SD | 6 | 5 | 83.33% | 15% |  | 30-34% | 6%
050100010000 | AUBURN CITY SD | 7 | 6 | 85.71% | 15% |  | 35-39% | 7%
030200010000 | BINGHAMTON CITY SD | 10 | 9 | 90% | 15% |  | 40-44% | 8%
062301040000 | BROCTON CSD | 2 | 0 | 0% | 5% |  | 45-49% | 9%
580203020000 | BROOKHAVEN-COMSEWOGUE UFSD | 6 | 0 | 0% | 5% |  | 50-54% | 10%
490202040000 | BRUNSWICK CSD (BRITTONKILL) | 2 | 1 | 50% | 10% |  | 55-59% | 11%
161601040000 | BRUSHTON-MOIRA CSD | 2 | 0 | 0% | 5% |  | 60-64% | 12%
140600010000 | BUFFALO CITY SD | 56 | 35 | 62.5% | 12% |  | 65-69% | 13%
222201060000 | CARTHAGE CSD | 5 | 1 | 20% | 5% |  | 70-74% | 14%
060401040000 | CASSADAGA VALLEY CSD | 2 | 0 | 0% | 5% |  | 75% or more | 15%
190401060000 | CATSKILL CSD | 3 | 3 | 100% | 15%
580513030000 | CENTRAL ISLIP UFSD | 8 | 4 | 50% | 10%
120401040000 | CHARLOTTE VALLEY CSD | 1 | 1 | 100% | 15%
110101040000 | CINCINNATUS CSD | 3 | 1 | 33.33% | 6%
650301040000 | CLYDE-SAVANNAH CSD | 3 | 1 | 33.33% | 6%
010500010000 | COHOES CITY SD | 5 | 0 | 0% | 5%
110200010000 | CORTLAND CITY SD | 6 | 2 | 33.33% | 6%
610301060000 | DRYDEN CSD | 5 | 2 | 40% | 8%
060800010000 | DUNKIRK CITY SD | 6 | 4 | 66.67% | 13%
500402060000 | EAST RAMAPO CSD (SPRING VALLEY) | 14 | 8 | 57.14% | 11%
180901040000 | ELBA CSD | 2 | 0 | 0% | 5%
070600010000 | ELMIRA CITY SD | 11 | 11 | 100% | 15%
590501060000 | FALLSBURG CSD | 2 | 1 | 50% | 10%
021601040000 | FRIENDSHIP CSD | 1 | 1 | 100% | 15%
460500010000 | FULTON CITY SD | 6 | 1 | 16.67% | 5%
430700010000 | GENEVA CITY SD | 4 | 3 | 75% | 15%
081401040000 | GEORGETOWN-SOUTH OTSELIC CSD | 1 | 1 | 100% | 15%
630300010000 | GLENS FALLS CITY SD | 5 | 1 | 20% | 5%
630918080000 | GLENS FALLS COMN SD | 1 | 0 | 0% | 5%
170500010000 | GLOVERSVILLE CITY SD | 6 | 4 | 66.67% | 13%
511101060000 | GOUVERNEUR CSD | 3 | 1 | 33.33% | 6%
042801060000 | GOWANDA CSD | 3 | 1 | 33.33% | 6%
010701030000 | GREEN ISLAND UFSD | 1 | 1 | 100% | 15%
610501040000 | GROTON CSD | 2 | 1 | 50% | 10%
250701040000 | HAMILTON CSD | 2 | 0 | 0% | 5%
460701040000 | HANNIBAL CSD | 3 | 3 | 100% | 15%
230301040000 | HARRISVILLE CSD | 2 | 0 | 0% | 5%
280201030000 | HEMPSTEAD UFSD | 10 | 7 | 70% | 14%
511301040000 | HERMON-DEKALB CSD | 1 | 1 | 100% | 15%
061700010000 | JAMESTOWN CITY SD | 9 | 5 | 55.56% | 11%
540901040000 | JEFFERSON CSD | 1 | 1 | 100% | 15%
031502060000 | JOHNSON CITY CSD | 4 | 2 | 50% | 10%
620600010000 | KINGSTON CITY SD | 10 | 4 | 40% | 8%
420807040000 | LAFAYETTE CSD | 3 | 0 | 0% | 5%
590901060000 | LIBERTY CSD | 2 | 2 | 100% | 15%
161501060000 | MALONE CSD | 5 | 2 | 40% | 8%
121401040000 | MARGARETVILLE CSD | 1 | 1 | 100% | 15%
541001040000 | MIDDLEBURGH CSD | 2 | 1 | 50% | 10%
051301040000 | MORAVIA CSD | 2 | 0 | 0% | 5%
240901040000 | MT MORRIS CSD | 2 | 1 | 50% | 10%
660900010000 | MT VERNON SCHOOL DISTRICT | 16 | 10 | 62.5% | 12%
650101060000 | NEWARK CSD | 5 | 2 | 40% | 8%
441600010000 | NEWBURGH CITY SD | 12 | 6 | 50% | 10%
400800010000 | NIAGARA FALLS CITY SD | 11 | 7 | 63.64% | 12%
651501060000 | NORTH ROSE-WOLCOTT CSD | 3 | 1 | 33.33% | 6%
170901040000 | NORTHVILLE CSD | 2 | 1 | 50% | 10%
411504020000 | NY MILLS UFSD | 2 | 0 | 0% | 5%
550101040000 | ODESSA-MONTOUR CSD | 3 | 0 | 0% | 5%
661500010000 | PEEKSKILL CITY SD | 6 | 3 | 50% | 10%
680601060000 | PENN YAN CSD | 3 | 1 | 33.33% | 6%
091200010000 | PLATTSBURGH CITY SD | 5 | 2 | 40% | 8%
441800050000 | PORT JERVIS CITY SD | 4 | 1 | 25% | 5%
131500010000 | POUGHKEEPSIE CITY SD | 7 | 6 | 85.71% | 15%
580602040000 | RIVERHEAD CSD | 7 | 6 | 85.71% | 15%
261600010000 | ROCHESTER CITY SD | 51 | 41 | 80.39% | 15%
043200050000 | SALAMANCA CITY SD | 3 | 2 | 66.67% | 13%
161201040000 | SALMON RIVER CSD | 4 | 1 | 25% | 5%
530600010000 | SCHENECTADY CITY SD | 17 | 14 | 82.35% | 15%
121601060000 | SIDNEY CSD | 3 | 0 | 0% | 5%
061501040000 | SILVER CREEK CSD | 3 | 0 | 0% | 5%
651201060000 | SODUS CSD | 3 | 1 | 33.33% | 6%
421800010000 | SYRACUSE CITY SD | 33 | 24 | 72.73% | 14%
491700010000 | TROY CITY SD | 7 | 2 | 28.57% | 5%
412300010000 | UTICA CITY SD | 13 | 7 | 53.85% | 10%
121901040000 | WALTON CSD | 3 | 2 | 66.67% | 13%
600101060000 | WAVERLY CSD | 5 | 1 | 20% | 5%
280401030000 | WESTBURY UFSD | 6 | 1 | 16.67% | 5%
262001040000 | WHEATLAND-CHILI CSD | 2 | 0 | 0% | 5%
170301020000 | WHEELERVILLE UFSD | 1 | 1 | 100% | 15%
472506040000 | WORCESTER CSD | 1 | 1 | 100% | 15%
580109020000 | WYANDANCH UFSD | 4 | 4 | 100% | 15%
662300010000 | YONKERS CITY SD | 39 | 10 | 25.64% | 5%
|  | 558 | 311