TABLE OF CONTENTS

TABLE OF CONTENTS

3    A Message from the Superintendent

4    Board of Education

5    Action Planning Team

6    District Profile

7    Mission and Vision

8-20   Strategic Goal Summaries

Goal Area #1: Attendance and Graduation Rate

Goal Area #2: Academics – Teaching and Learning

Goal Area #3: Student Engagement

Goal Area #4: Facilities and Operations

Goal Area #5: Finance/Budget

21   Acknowledgements

3    A Message from the Superintendent

4    Board of Education

5    Action Planning Team

6    District Profile

7    Mission and Vision

8-20   Strategic Goal Summaries

Goal Area #1: Attendance and Graduation Rate

Goal Area #2: Academics – Teaching and Learning

Goal Area #3: Student Engagement

Goal Area #4: Facilities and Operations

Goal Area #5: Finance/Budget

21   Acknowledgements

A MESSAGE FROM THE SUPERINTENDENT

McLoud Public Schools’ 2018-2022 Comprehensive Strategic Plan is designed to provide a road map of excellence that the district will use to inform and define transformation and cultural change. Our district takes great pride in the importance and value of education we provide to our students. Parents, community members, students, and district employees have high expectations in preparing our students for college/career readiness. The plan will guide the district in our quest to provide the highest quality of education that our students and community expect.

The plan is the framework through which the district supports schools to ensure the academic success of each student. This framework allows progress to be measured, priorities established, resources allocated, and communications improved among all stakeholders. The goals, objectives, initiatives and action steps will be continually monitored, and the Board of Education will be regularly updated as to the implementation and progress of the plan.

Thank you to all who participated in the strategic planning process. I am appreciative for all the time, hard work, and commitment given by many in the development of this plan.

Mr. Steve Stanley

Superintendent

3

BOARD OF

EDUCATION

Melanie Krause - President

Dustin Greenberg – Vice President

Bobby Howard - Clerk

Doug Vanscoyoc – Deputy Clerk

Joe Nolen - Member

4

# ACTION PLANNING TEAM

Steve Stanley - Superintendent

Jami Eddings - Director of Student Services

Patty Stanley - Director of Special Services

Rhonda Hockenbury - High School Principal

Bryan Jennings - Assistant High School Principal

Melanne Greenwood - Jr. High Principal

Julie Wolffrum - Assistant Jr. High Principal

Angela Drew - Intermediate Principal

Christina Gilliam - Intermediate Dean of Students

Andrew Winters - Elementary Principal

Sally Thomason - Early Childhood Center Principal

5

# DISTRICT PROFILE

DISTRICT REVENUES: (ALL FUNDS)

LOCAL / COUNTY: $2,233,045 STATE: $9,523,946 FEDERAL: 1,268,067

130 TEACHERS 13 ADMINISTRATORS 100 SUPPORT STAFF

Administrators – 92% advanced degrees, 22.5 average years’ experience

Teachers - 24% with advanced degrees, 11.3 average years teaching experience

Enrollment Trends 		   	                 Ethnicity

6

# MISSION AND VISION

OUR MISSION:

Working together with families and community to provide a safe, quality education that builds relationships while engaging and challenging all students.

OUR VISION:

Our district empowers all students to embrace learning.

7

STRATEGIC GOALS

SUMMARY

GOAL AREA #1: Attendance and Graduation Rate

OBJECTIVE 1:  INCREASED AWARENESS

» Initiative 1:  Create a positive culture for increasing student attendance

» Initiative 2:  Increase student attendance and graduation rate

OBJECTIVE 2:  IMPROVE CHRONIC ABSENTEEISM

» Initiative 1:  Implement a system to identify students who are

chronically absent

» Initiative 2:  Implement strategies to improve chronic absenteeism

GOAL AREA #1: Attendance and Graduation Rate

OBJECTIVE 1:  INCREASED AWARENESS

» Initiative 1:  Create a positive culture for increasing student attendance

» Initiative 2:  Increase student attendance and graduation rate

OBJECTIVE 2:  IMPROVE CHRONIC ABSENTEEISM

» Initiative 1:  Implement a system to identify students who are

chronically absent

» Initiative 2:  Implement strategies to improve chronic absenteeism

GOAL AREA #1

Attendance and Graduation Rate

OBJECTIVE 1: INCREASED AWARENESS

INITIATIVE 1:  Create a positive culture for increasing student attendance

ACTION STEPS:								            TIMELINE:

Create a district wide slide show to be presented at Back to School Night			Fall 2019

Review/Align Board Policy and Student Handbook					2019-2020

Parents/Guardians will receive phone calls (School Messenger) concerning		2018-2022

attendance

Implement High School Orientation for Freshman 			  		2019-2022

Use Social Media (Twitter, Live Feed, Facebook, Digital Billboards) 			2019-2022

8

Send letters to notify parents/guardians		                                                     		Throughout the

Year

Parents/Guardians sign an Attendance Policy						2019-2022

Superintendent and administration will meet to develop a process to			2019-2020

monitor absenteeism and graduation rate

Board Policy for attendance will be reviewed and aligned with Student Handbook	2019-2020

Measure(s) – Growth for attendance and graduation rate will be indicated on the OSDE

School Report Card.

INITIATIVE 2: Increase student attendance and graduation rate

ACTION STEPS:									TIMELINE:

Provide test exemption incentives							2019-2022

Place Posters in the hallways showing attendance and graduation rates			Fall 2019

Provide 9 weeks attendance awards							2019-2022

Teachers/Staff will use positive rewards/incentives to increase attendance		2019-2022

Implement attendance reward trips							2019-2022

Create attendance Bulletin Boards in each building					Throughout the

School Year

By 2022, overall attendance rate will increase by 10% as measured by district records

and/or state results.

By 2022, overall graduation rate will increase by 5% in the high school as measured by district

records and/or state results.

OBJECTIVE 2: IMPROVE CHRONIC ABSENTEEISM

INITIATIVE 1: Implement a system to identify students who are chronically absent

ACTION STEPS:										TIMELINE:

Kickapoo Tribe partnership/support							2018-2022

Implement a high school committee for chronic absenteeism				Fall 2019

9

Research/create an Early Warning System						2019-2020

Implement an Early Warning System							2020-2021

Develop a process to monitor and evaluate the chronic absenteeism system	              	2019-2020

INITIATIVE 2: Implement strategies to improve chronic absenteeism

ACTION STEPS:										TIMELINE:

All teachers will attend professional development on creating and implementing		2019-2020

an Early Warning System

Review the Board Policy	 and revise as needed					              2018-2022

County CAB Process									2018-2022

Provide time for students with chronic absences to make work up (Saturday School,	2019-2020

After School, during school, etc.)

Develop a process to monitor strategies implemented in the district, school and		2019-2020

classroom

By 2022, the overall chronic absenteeism rate will decrease by 10% based on results from the OSDE School Report Card.

GOAL AREA #2: Academics – Teaching and Learning

OBJECTIVE 1:  INCREASE STUDENT ACHIEVEMENT

» Initiative 1:  Create and implement Response to Intervention (RTI)

programs in reading and math

» Initiative 2:  Continue to create and build district curriculum

aligned with the Oklahoma Academic Standards

OBJECTIVE 2:  INCREASE RIGOR OF INSTRUCTION

» Initiative 1:  Use Higher Order Thinking Skills

» Initiative 2:  Use Project Based Learning

OBJECTIVE 3:  CREATE A COLLEGE AND CAREER READY CULTURE

» Initiative 1:  Prepare students for College and/or Career Readiness

» Initiative 2:  ICAP

GOAL AREA #2: Academics – Teaching and Learning

OBJECTIVE 1:  INCREASE STUDENT ACHIEVEMENT

» Initiative 1:  Create and implement Response to Intervention (RTI)

programs in reading and math

» Initiative 2:  Continue to create and build district curriculum

aligned with the Oklahoma Academic Standards

OBJECTIVE 2:  INCREASE RIGOR OF INSTRUCTION

» Initiative 1:  Use Higher Order Thinking Skills

» Initiative 2:  Use Project Based Learning

OBJECTIVE 3:  CREATE A COLLEGE AND CAREER READY CULTURE

» Initiative 1:  Prepare students for College and/or Career Readiness

» Initiative 2:  ICAP

10

GOAL AREA #2

Academics – Teaching and Learning

OBJECTIVE 1: INCREASE STUDENT ACHIEVEMENT

INITIATIVE 1:  Create and implement Response to Intervention (RTI) programs in reading

and math

ACTION STEPS:								            TIMELINE:

Administer district aligned benchmarks K-12 grades to determine which			Beginning,

students need instructional interventions						Middle, and

End of each Year

Create a districtwide reading Response to Intervention (RTI) program			2019-2020

by using teaching interventions and evidence-based practices that researchers

have studied and shown to be effective

Pre-K through 12th grade teachers implement small group instruction tailored for	2018-2022

different skills levels and/or learning styles

Teachers will progress monitor and frequently assess each student’s skill ability to	2018-2022

determine whether an intervention is effective	Ongoing throughout each Year

Create a districtwide math Response to Intervention (RTI) program by using 		2019-2020

teaching interventions and evidence-based practices that researchers have		Ongoing

studied and shown to be effective							throughout

each Year

K-8th grade teachers will implement Response to Intervention (RTI) with students	2019-2022

who need additional support in math for 15-30 minutes or more as needed each day	Ongoing

throughout

each Year

Teachers in grades 9 through 12 will implement Response to Intervention (RTI)		2019-2022

with students who need additional support in math one-time each week			Weekly

Build math fluency districtwide using evidence-based best practices			2019-2022

Build achievement with our English Language Learners					2018-2022

11

Increase parental involvement in the student learning process				2018-2022

Ongoing

throughout

each Year

By 2022, the overall reading and math performance of students in need of

Response to Intervention (RTI) overall performance in reading and math will increase

as measured by the NWEA Map Assessments and RIT scores.

INITIATIVE 2:  Continue to create and build district curriculum aligned with the

Oklahoma Academic Standards (OAS)

ACTION STEPS:								            TIMELINE:

Teachers will develop and/or revise curriculum maps in reading and math		2018-2022

aligned with the Oklahoma Academic Standards during PLC’s			Ongoing

throughout

each Year

Teachers will develop and/or revise curriculum maps in science and		2019-2021

social studies during PLC’s								Ongoing

throughout

each Year

Teachers will review the OSDE Curriculum Frameworks				2019-2022

Teachers at all grade levels will develop/revise curriculum maps and		2019-2022

vertically align with the Oklahoma Academic Standards during Professional

Development Days, teacher release time, and/or grade level team meetings

Assistance and training will be provided to all teachers to support 			2019-2022

development/revision of curriculum maps						Ongoing

throughout

each Year

The Curriculum and Assessment Director/Coordinator will provide			2018-2022

support and assist administration and teacher teams to develop/revise		Ongoing

curriculum maps									throughout

each Year

Teachers will use Common Formative Assessments (CFA’s) to monitor		2019-2022

student performance and growth							Ongoing

throughout

each Year

12

Teacher leaders may seek outside professional development focused on		2019-2022

Creating Common Formative Assessments (CFA’s)					Ongoing

throughout

each Year

By the end of the 2022 school year, 90% teachers will have received training

in curriculum alignment with the Oklahoma Academic Standards and creating

Common Formative Assessments so that students master state standards.

OBJECTIVE 2: INCREASE RIGOR OF INSTRUCTION

INITIATIVE 1:  Use Higher Order Thinking Skills

ACTION STEPS:								            TIMELINE:

Provide professional development for all teachers on using Higher Order		2019-2020

Thinking (HOT) Skills

Use Professional Learning Communities (PLC’s) to research and develop		2019-2022

Higher Order Thinking strategies to implement with all learners

Teachers will use Bloom’s and Webb’s Depth of Knowledge Levels with		2018-2022

Questioning strategies to create higher level thinking with all learners

Develop a process to monitor the effectiveness of using Higher Order		2019-2020

Thinking skills in the classroom (Administration Focus Walks, data results)

13

INITIATIVE 2:  Use Project Based Learning

ACTION STEPS:								            TIMELINE:

Professional development will be provided for all teachers on using 	         August 2, 2019

Learning (PBL) activities by Collier Education Consulting, L.L.C.

Provide professional development for all teachers on Unit Planning		2019-2020

Teachers will integrate Project Based Learning activities/units into curriculum	2020-2022

maps

Teachers will integrate PBL activities throughout each year				2020-2022

Develop a process to monitor the effectiveness of using Project Based		2019-2020

Learning activities/units in the classroom

OBJECTIVE 3: CREATE A COLLEGE AND CAREER READY CULTURE

INITIATIVE 1:  Prepare students for College and/or Career Readiness

ACTION STEPS:								            TIMELINE:

Create college and career interests for 7th and 8th grade students			2019-2022

College visits (7th and 8th grade students)						2019-2022

Gordon Cooper (8th grade students) - Oklahoma Promise				2018-2022

College Fair (Juniors and Seniors)							2019-2022

Career Fair										2019-2022

Provide FAFSA Support for High School Students					2018-2022

Promote Parental Involvement 							2018-2022

Measure(s) – By 2022, college and career interests for 7th and 8th grade students will

be created and implemented.

14

INITIATIVE 2:  ICAP

ACTION STEPS:								            TIMELINE:

District team attended OSDE ICAP training						2018-2019

ICAP Kick-off meeting to build awareness					        August 28, 2018

Pilot the ICAP with 9th grade students						2019-2020

ACT Prep Course will be implemented						2020-2021

Student Data Trackers/Portfolios will be used 					2020-2022

Measure(s) – By 2022, ICAPs with all students in grades 9-12 will be implemented.

15

GOAL AREA #3: Student Engagement

OBJECTIVE 1:  Active Engagement

» Initiative 1:  Students will be engaged in the learning process

» Initiative 2:  Individualized learning will be provided

GOAL AREA #3: Student Engagement

OBJECTIVE 1:  Active Engagement

» Initiative 1:  Students will be engaged in the learning process

» Initiative 2:  Individualized learning will be provided

GOAL AREA #3

Student Engagement

OBJECTIVE 1: Active Engagement

INITIATIVE 1:  Students will be engaged in the learning process

ACTION STEPS:									TIMELINE:

Professional development will be provided for all teachers in the following

Areas:

·        Engaging students in the learning process					2019-2020

·        Cooperative Learning - Kagan						            August 2, 2019

Collier Education Consulting, L.L.C., will provided onsite training

·        Project Based Learning							            August 2, 2019

Collier Education Consulting, L.L.C., will provide onsite training	            Ongoing

Throughout

Each Year

·        Real World Connections							   	2018-2022

·        Peer Teaching/Mentoring will be implemented using Instructional		2019-2022

Rounds

Student engagement will be measured by walkthroughs, observation of implementation of

differentiated instructional strategies in the classroom, student questioning and lesson plans.

16

INITIATIVE 2:  Individualized learning will be provided

ACTION STEPS:									TIMELINE:

1:1 technology for all students (PK-12)                                                                           	2019-2020

Google Classroom training will be provided for teachers			            August 2, 2018

Ongoing

Throughout

Each Year

Modules for teachers will be provided 						2019-2020

Ken Thompson

Individual student goals and data will be utilized to promote growth		2019-2022

with all students (NWEA Map assessments)

Measure(s) – Individualized learning will be measured by goals and data using

NWEA Map assessments to determine growth.

17

OBJECTIVE 1:  Provide Increased Access to Up-to-Date Technology

» Initiative 1:  Improved infrastructure

» Initiative 2:  Improved technology maintenance

OBJECTIVE 2:  Ensure Safe School Environment

» Initiative 1:  To build a comprehensive Safety Plan for McLoud Public

Schools

OBJECTIVE 3:  Provide Well-Maintained Buildings and Grounds

» Initiative 1:  Replacements of building roofs, HVAC units, and district

lighting systems

GOAL AREA #4

Facilities and Operations

OBJECTIVE 1: PROVIDE INCREASED ACCESS TO UP-TO-DATE TECHNOLOGY

INITIATIVE 1: Improved infrastructure

ACTION STEPS:									TIMELINE:

360 Chromebooks									Fall 2018

One-to-one										2019-2020

INITIATIVE 2: Improved technology maintenance

ACTION STEPS:									TIMELINE:

Develop a process for improved technology maintenance with a 			2019-2020

district committee

18

OBJECTIVE 2: ENSURE SAFE SCHOOL ENVIRONMENT

INITIATIVE 1: To build a comprehensive Safety Plan for McLoud Public Schools

ACTION STEPS:									TIMELINE:

Work with Jason Gray (OSDE) to build a comprehensive Safety Plan		2019-2020

Phase I – Six Step Process for safety concerns		               	         August 26, 2019

OBJECTIVE 3: PROVIDE WELL-MAINTAINED BUILDINGS AND GROUNDS

INITIATIVE 1: Replacements of building roofs, HVAC units, and district lighting systems

ACTION STEPS:									TIMELINE:

Maintenance of building roofs, HVAC units, and district lighting will be		2018-2022

monitored throughout each year

Previous Bond – New Intermediate School						Spring 2018-

Fall 2019

Proposed Bond facility improvements – Paving Athletic Parking Lot,	      August-November

New Track, New Board Office, Athletic Fields, Redo Concession/Restroom		 2019

19

GOAL AREA #5: Finance and Budget

OBJECTIVE 1:  Align Expenditures to Goal Areas

» Initiative 1:  Comprehensive Strategic Planning Process

OBJECTIVE 2:  Seek Alternative Funding

» Initiative 1:  Additional funding for goal area objectives

GOAL AREA #5: Finance and Budget

OBJECTIVE 1:  Align Expenditures to Goal Areas

» Initiative 1:  Comprehensive Strategic Planning Process

OBJECTIVE 2:  Seek Alternative Funding

» Initiative 1:  Additional funding for goal area objectives

GOAL AREA #5

GOAL AREA #5

Finance and Budget

OBJECTIVE 1: ALIGN EXPENDITURES TO GOAL AREAS

INITIATIVE 1: Comprehensive Strategic Planning Process

ACTION STEPS:									TIMELINE:

Determine who will present the Comprehensive Strategic Plan overview                 2018

Kim Collier – Collier Education Consulting, L.L.C.

Present 5 Year Plan to the McLoud Board of Education                                       November 14, 2019

Kim Collier – Collier Education Consulting, L.L.C.

Measure(s) - Support all of goal area objectives as identified by the Board of Education by 2022.

OBJECTIVE 2: SEEK ALTERNATIVE FUNDING

INITIATIVE 1: Additional Funding for Goal Area Objectives

ACTION STEPS:									TIMELINE:

Administrators will contact possible donors for alternative funding of goal 	2019-2022

area objectives

Develop a schedule and share opportunities found with Board of Education   	2019-2022

and site principals

Measure(s) – Possible donations from donors will be identified and schedule(s) shared                                                                                                    with the Board of Education as needed                                                                                                20

Acknowledgements

Collier Education Consulting, L.L.C. commends the McLoud Public School District, Board of Education and members of the Action Planning Team in this commitment toward comprehensive strategic planning and improvement. Through this process, a five-year strategic plan, aligned to the district’s vision, mission, and core values, has been developed to provide guidance for McLoud Public Schools’ decision making and actions in the future. We also would like to acknowledge the dedication of the Avedis Foundation and support they have provided toward educational improvement.

21